## Sheet1
Risk type | Risks | Probability | Impact | Zone | Approach
Technical | Requirements inflation which introduces new features which were not identified during planning phase. These new features threaten project time estimations. | High | High |  | Mitigation. Project Manager has to communicate effectively with project sponsors as well as project team to ensure that new requirements are suitable and does not severely impact project timeline.
| Poor quality of code given resulting in higher frequency of crashes and inability to handle edge cases. Poor quality code also increases the difficulty of implementing new features. | Medium | High |  | Avoidance. Experienced team members will be paired with inexperienced team members to do pair coding as well as code review. This helps to ensure that code written is of good quality.
| Lack of end-user engagement which can advise the features that are needed or those that are redundant during software development. | Medium | Medium |  | Mitigation. Developers have to communicate with end-users more effectively and consistently to ensure time is not wasted on redundant features.
Management | Poor productivity which results from lack of sense of urgency to work in earnest due to long project timelines in the earlier stages. | Low | High |  | Mitigation. Project deliverables to be submitted at the end of every sprint helps to keep the project team on their toes and constantly deliver work.
| Poor estimation of project timelines and workload due to unforeseen features and risks | Medium | Medium |  | Mitigation. Team members have to communicate and collaborate consistently such that everyone is updated on project progress. It is important to also allow for extra time for timeline estimation during project planning to take into account unforeseen factors.
| Health issues which may result in missing key team members during critical times, which may affect code quality and efficiency. | Low | Medium |  | Acceptance. It is not possible to have all team members be healthy and illnesses may arise due to global events or flu season. However, the impact can be mitigated by adopting code sharing practices and pair coding to ensure that the project does not suffer derailment should a key member be unavailable.