## Instructions
Activities During the Planning Meet:
| Estimated Task Priority: | Each team member select a value between 0 (most unimportant) to 10 (most important) from the drop down list based on his/her own understanding about the task.
| Estimated Task Difficulty: | Each team member select a value between 0 (extremely easy) to 10 (extremely difficult) from the drop down list based on his/her own understanding about the task.
| Estimated Task Time Required: | Each team member select a value between 1 to 14 days from the drop down list based on his/her own understanding about the task.
| Confidence about the Task: | Each team member select a value between 0 (not confident at all) to 10 (extremely confident) from the drop down list based on his/her own understanding about the task and his/her own capabilities.
| Assignee's Mood: | Excited | Happy | Neutral | Sad | Depressed
| Task Assignee: | Team members should discuss among themselves to distribute the tasks. If there are tasks which remain unassigned after the discussion, team lead will decide to whom the remaining task(s) should be delegated.
Activities During the Subsequent Planning Meeting
Review for each task: if it has been completed (Yes/No), rate the quality of the result (0: Extremely Bad -10: Excellent)

## BackLog
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers
|  |  | Kenny | Wilson | Hou Jing | ZeYu | Irsyad | Boon | -
Team member's mood during the this week's meeting: |  |  | Neutral | Neutral | Happy | Neutral | Neutral | Neutral | Neutral
1 | Use Case Model | Task Quality Evaluation (After Task Completed) | 7 | 8 | 8 | 8 | 8 | 8 |  | 8 | 6.1667 | 8.3333 | Kenny
| Estimated Task Priority（0-10） |  | 8 | 8 | 8 | 8 | 8 | 8
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 7 | 10 | 9 | 8 | 8
| Team Member's Confidence about the Task (0-10) |  | 6 | 7 | 7 | 7 | 7 | 6
2 | Project Proposal | Task Quality Evaluation (After Task Completed) | 7 | 8 | 8 | 8 | 8 | 8 |  | 9.3333 | 6.1667 | 9.3333 | Wilson | Kenny, Hou Jing, Zeyu, Irsyad
| Estimated Task Priority（0-10） |  | 9 | 9 | 10 | 10 | 10 | 8
| Estimated Task Difficulty（0-10） |  | 6 | 7 | 6 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 10 | 9 | 10 | 10 | 10 | 7
| Team Member's Confidence about the Task (0-10) |  | 8 | 10 | 7 | 8 | 8 | 8
3 | Quality Plan | Task Quality Evaluation (After Task Completed) | 7 | 8 | 7 | 8 | 7 | 7 |  | 8.3333 | 6.5 | 9.5 | Boon
| Estimated Task Priority（0-10） |  | 8 | 9 | 8 | 9 | 8 | 8
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 7 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 10 | 8 | 10 | 10 | 11 | 8
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 7 | 9 | 7 | 7
4 | SRS | Task Quality Evaluation (After Task Completed) | 7 | 8 | 7 | 8 | 8 | 8 |  | 9.6667 | 8.1667 | 10.8333 | Wilson
| Estimated Task Priority（0-10） |  | 10 | 10 | 9 | 10 | 10 | 9
| Estimated Task Difficulty（0-10） |  | 8 | 9 | 8 | 8 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 11 | 8 | 12 | 12 | 12 | 10
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 7 | 7 | 8 | 7
5 | Dialog Map | Task Quality Evaluation (After Task Completed) | 8 | 8 | 8 | 8 | 8 | 7 |  | 6.5 | 5 | 5.8333 | Hou Jing | Irsyad
| Estimated Task Priority（0-10） |  | 6 | 7 | 7 | 6 | 6 | 7
| Estimated Task Difficulty（0-10） |  | 5 | 5 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 6 | 6 | 6 | 6 | 6
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 8 | 0 | 8 | 8
6 | ER Diagram | Task Quality Evaluation (After Task Completed) | 7 | 8 | 8 | 8 | 8 | 8 |  | 6 | 5.5 | 5.6667 | ZeYu
| Estimated Task Priority（0-10） |  | 6 | 5 | 7 | 6 | 6 | 6
| Estimated Task Difficulty（0-10） |  | 5 | 5 | 6 | 5 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 6 | 7 | 5 | 5 | 6
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 7 | 8 | 7 | 7
7 | Project Plan | Task Quality Evaluation (After Task Completed) | 8 | 9 | 9 | 8 | 9 | 9 |  | 7.6667 | 6.5 | 8.5 | Kenny
| Estimated Task Priority（0-10） |  | 7 | 8 | 7 | 8 | 8 | 8
| Estimated Task Difficulty（0-10） |  | 6 | 7 | 7 | 6 | 7 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 9 | 10 | 8 | 8 | 9 | 7
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 8 | 8 | 8 | 8
8 | Risk Management | Task Quality Evaluation (After Task Completed) | 8 | 8 | 9 | 8 | 9 | 9 |  | 6.8333 | 7 | 7.6667 | Boon | wilson
| Estimated Task Priority（0-10） |  | 7 | 6 | 7 | 7 | 7 | 7
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 8 | 6 | 8 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 6 | 9 | 7 | 8 | 8
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 8 | 8 | 8 | 7
9 | Report on software maintainability | Task Quality Evaluation (After Task Completed) | 8 | 8 | 7 | 8 | 8 | 8 |  | 6.8333 | 6.6667 | 5.5 | Wilson
| Estimated Task Priority（0-10） |  | 7 | 6 | 6 | 8 | 7 | 7
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 5 | 8 | 6 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 6 | 5 | 6 | 6 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 7 | 8 | 8 | 9
10 | Configuration management plan | Task Quality Evaluation (After Task Completed) | 9 | 8 | 8 | 9 | 8 | 8 |  | 8.1667 | 7.5 | 7.5 | Kenny
| Estimated Task Priority（0-10） |  | 8 | 9 | 8 | 8 | 8 | 8
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 7 | 8 | 7 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 8 | 7 | 8 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 7 | 9 | 7 | 8 | 8
11 | Change management plan | Task Quality Evaluation (After Task Completed) | 8 | 9 | 8 | 8 | 7 | 9 |  | 7.6667 | 8.3333 | 8.5 | Irsyad
| Estimated Task Priority（0-10） |  | 8 | 7 | 8 | 8 | 7 | 8
| Estimated Task Difficulty（0-10） |  | 8 | 9 | 9 | 8 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 9 | 8 | 9 | 8 | 8 | 9
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 8 | 8 | 9 | 8
12 | Release plan | Task Quality Evaluation (After Task Completed) | 8 | 9 | 8 | 9 | 8 | 8 |  | 8.8333 | 8.6667 | 8.5 | Hou Jing
| Estimated Task Priority（0-10） |  | 9 | 9 | 8 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 9 | 8 | 8 | 9 | 9 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 9 | 9 | 8 | 8 | 9
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 8 | 9 | 8 | 7
13 | Test plan | Task Quality Evaluation (After Task Completed) | 8 | 8 | 8 | 9 | 8 | 8 |  | 8.8333 | 8.1667 | 8.5 | Boon
| Estimated Task Priority（0-10） |  | 9 | 9 | 8 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 7 | 9 | 9 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 9 | 9 | 8 | 8 | 9
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 8 | 8 | 8 | 7
14 | Test cases and requirement test coverage | Task Quality Evaluation (After Task Completed) | 8 | 8 | 8 | 9 | 8 | 8 |  | 8.5 | 8 | 8.1667 | Boon
| Estimated Task Priority（0-10） |  | 7 | 9 | 8 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 7 | 9 | 9 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 9 | 9 | 8 | 8 | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 8 | 8 | 8 | 8
15 | CMMI | Task Quality Evaluation (After Task Completed) | 8 | 8 | 8 | 9 | 8 | 8 |  | 8.5 | 7.8333 | 8 | ZeYu
| Estimated Task Priority（0-10） |  | 7 | 9 | 8 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 8 | 7 | 7 | 9 | 9 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 9 | 9 | 8 | 8 | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 8 | 8 | 8 | 8
16 | Powerpoint | Task Quality Evaluation (After Task Completed) | 8 | 8 | 8 | 9 | 8 | 8 |  | 9 | 8.3333 | 8.6667 | Kenny | Kenny, Hou Jing, Zeyu, Irsyad, boon
| Estimated Task Priority（0-10） |  | 10 | 9 | 8 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 8 | 7 | 10 | 9 | 9 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 9 | 9 | 9 | 8 | 8 | 9
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 9 | 9 | 10 | 8